## Slide 1: Software Engineering
Week 02 Lecture 01

## Slide 2: Software Project Management
Concerned with activities involved in ensuring that software is delivered on time and on schedule and in accordance with the requirements of the customer organization.
Project management is needed because software development is always subject to budget and schedule constraints that are set by the organization developing the software.

## Slide 3: Success criteria for project
Deliver the software to the customer at the agreed time.
Keep overall costs within budget.
Deliver software that meets the customer’s expectations.
Maintain a happy and well-functioning development team.

## Slide 4: Software management distinctions
The product is intangible.
Many software projects are 'one-off' projects.
Software processes are variable and organization specific.
Notes: Software cannot be seen or touched. Software project managers cannot see progress by simply looking at the artefact that is being constructed.
Large software projects are usually different in some ways from previous projects. Even managers who have lots of previous experience may find it difficult to anticipate problems.
We still cannot reliably predict when a particular software process is likely to lead to development problems.

## Slide 5: Software management activities
Project planning
Reporting
Risk management
People management
Proposal writing
Notes: Project managers are responsible for planning. estimating and scheduling project development and assigning people to tasks.
Project managers are usually responsible for reporting on the progress of a project to customers and to the managers of the company developing the software.
Project managers assess the risks that may affect a project, monitor these risks and act when problems arise.
Project managers have to choose people for their team and establish ways of working that leads to effective team performance
The first stage in a software project may involve writing a proposal to win a contract to carry out an item of work. The proposal describes the objectives of the project and how it will be carried out.

## Slide 6: Risk management
A risk is a probability that some adverse circumstance will occur
Identifying risks and drawing up plans to minimize their effect on a project.
  Project risks affect schedule or resources
  Product risks affect the quality or performance of the software being developed;
  Business risks affect the organization developing or procuring the software.

## Slide 7: Examples of common project, product, and business risks
Risk | Affects | Description
Staff turnover | Project | Experienced staff will leave the project before it is finished.
Management change | Project | There will be a change of organizational management with different priorities.
Hardware unavailability | Project | Hardware that is essential for the project will not be delivered on schedule.
Requirements change | Project and product | There will be a larger number of changes to the requirements than anticipated.
Specification delays | Project and product | Specifications of essential interfaces are not available on schedule.
Size underestimate | Project and product | The size of the system has been underestimated.
CASE tool underperformance | Product | CASE tools, which support the project, do not perform as anticipated.
Technology change | Business | The underlying technology on which the system is built is superseded by new technology.
Product competition | Business | A competitive product is marketed before the system is completed.

## Slide 8: Risk management process
Risk identification
Risk analysis
Risk planning
Risk monitoring
Notes: Identify project, product and business risks;
Assess the likelihood and consequences of these risks;
Draw up plans to avoid or minimize the effects of the risk;
Monitor the risks throughout the project;

## Slide 9: Managing people
People are an organization's most important assets.
The tasks of a manager are essentially people-oriented. Unless there is some understanding of people, management will be unsuccessful.
Poor people management is an important contributor to project failure.

## Slide 10: Personality types
The manager should consider different personality types:
Task-oriented
Self-oriented
Interaction-oriented.
Notes: The motivation for doing the work is the work itself;
The work is a means to an end, which is the achievement of individual goals - e.g., career progress.
The principal motivation is the presence and actions of co-workers. People go to work because they like to go to work.

## Slide 11: Project scheduling
Organizing tasks separately and executing
Estimate time
Identify resources
Identify people/team
Notes: Project scheduling is the process of deciding how the work in a project will be organized as separate tasks, and when and how these tasks will be executed.
You estimate the calendar time needed to complete each task, the effort required and who will work on the tasks that have been identified.
You also have to estimate the resources needed to complete each task, such as the disk space required on a server, the time required on specialized hardware, such as a simulator, and what the travel budget will be.

## Slide 12: Project scheduling
Split project into tasks
Organize tasks concurrently
Minimize task dependencies
Project manager’s intuition and experience.
Notes: Split project into tasks and estimate time and resources required to complete each task.
Organize tasks concurrently to make optimal use of workforce.
Minimize task dependencies to avoid delays caused by one task waiting for another to complete.
Dependent on project managers intuition and experience.

## Slide 13: Milestones and deliverables
Milestones are points in the schedule against which you can assess progress.
Deliverables are work products that are delivered to the customer.
Notes: 1- for example, the handover of the system for testing.
2- , e.g., a requirements document for the system.

## Slide 14: Tasks, start date, end date and duration
Project Task | Start Date | End Date | Duration
Analysis | 1/1/2023 | 1/8/2023 | 7
Design | 1/8/2023 | 1/23/2023 | 15
Development | 1/23/2023 | 2/5/2023 | 13
Testing | 2/5/2023 | 2/10/2023 | 5
Customer acceptance | 2/10/2023 | 2/18/2023 | 8
Maintenance | 2/18/2023 | 2/25/2023 | 7
https://www.youtube.com/watch?v=xsxi4qaEnOg

## Slide 15: Gantt chart

## Slide 16: Work Breakdown Structures (WBS)
WBS is a hierarchical decomposition of a project into smaller, more manageable components.
These components are called work packages
Work packages can be further subdivided into smaller, more detailed components
Notes: The WBS typically consists of several levels, each of which represents a different level of detail in the project. The top level is usually the project itself, with subsequent levels representing major deliverables, phases, tasks, and subtasks. Each level should be broken down into manageable and well-defined components, which can be assigned to individual team members or groups.

## Slide 17: Purpose of WBS
To help organize and define the scope of a project
To identify the tasks and activities required to complete the project
To establish a clear and concise structure for the project team to follow
Completion on time, within budget, and to the satisfaction of stakeholders.

## Slide 18: Example of WBS
We will be designing a simple Learning Management System. The system will allow students, teacher, admin and exam dept. to sign-in to their accounts. Students can register in more than one subjects in one semester while admin will offer the semester and subjects in that semester. Students can view their DMC while Teacher can add results. Students can view their dues summary while exam branch can edit, generate the dues. Administrator can update, change the account information of both teachers and students.

## Slide 19: Example of WBS

## Slide 20: WHAT HAVE YOU LEARNT IN THIS CLASS
Software Project Management
Success criteria for project
Software Management Activities
Develop a Software according to the Design
Gannt charts
WBS